## Sheet1
HSBC
Sl. No. | Branch Name | Address | Branch Name | Address | Link Up Date | Link Status | Remarks
1 | Hotel Radisson ATM Booth | Hotel Radisson, Staff Road, Airport Road, Dhaka Cantonment, Dhaka. | Dhanmondi ATM Booth | Momtaz Plaza, House # 07, Road # 4, (Gr. Fl.) Dhanmondi | X | Pending | Our Management didn't give permission to work for this link.
2 | BFC ATM Booth | BFC, Gulshan - 2, Dhaka. | Hotel Westin ATM Booth | Plot 3 1, Road 3 45, Gulshan-2, Dhaka. | x | Pending | Successfully Done and Acceptance Paper Signed.
3 | Chittagong EPZ ATM Booth |  | Jamal Khan ATM Booth | Equity Millennium, 59 Jamal Khan Road, Chittagong | x | Pending | Mr. Afjal didn't get the servey report of this link from CTG.
4 | Sylhet Zindabazar office |  | Uposhohar ATM Booth | Rose View Complet, Shahjalal Uposhohar Road, Sylhet. |  | Pending | Cabling Work Completed but Fusion work pending because our head office didn't send work costing money to Mr. Arnob of our Sylhet Office.
5 | Shantinagar Offsite ATM Booth | Twin Tower Concord, Shantinagar, Dhaka. | Chawk Bazar New SME CSE, | 203 Water Works Raod, Lalbagh, Dhaka. | 2008-06-15 | Work Completed | Successfully Done and Acceptance Paper Signed.
6 | Banani Branch | House # 155 (New) 55 (Old), Road # 11, Banani, Dhaka. | Dhanmondi Branch | House # 352 (Old), Dhanmondi, Dhaka. | 2008-06-08 | work Completed | Successfully Done and Acceptance Paper Signed.
7 | Banani Branch | House # 155 (New) 55 (Old), Road # 11, Banani, Dhaka. | Motijheel Branch | 1/C, Rajuk Avenue, Motijheel C/A, Dhaka. | 2008-06-11 | work Completed | Successfully Done and Acceptance Paper Signed.