## 1 Cover page
[7 empty] | Cover page | 1
[7 empty] | Test page | 2
[7 empty] | Snag | 1
[7 empty] | PAT | 1
[7 empty] | Total page | 5
Please print entire workbook
PRELIMINARY ACCEPTANCE TEST - ATP
BTS
| Country: | Bangladesh
| Operator: | AccessTel
| Project: | WiMAX Deployment
| ATP DATE |  | :
| SITE ID |  | :
| SITE NAME |  | :
| SITE ADDRESS |  | :
| SUPERVISOR |  | :
Section Revision History
|  |  | Document No. |  | Doc. Rev | Page
|  |  | BD-H&NM-AC-SF-ICICHECK |  | 0 | 1 of 3

## 2 Installation Check list
Installation Check list
Date |  | 0
Site ID |  | 0
Site Name |  | 0
Supervisor Name |  | 0
Item No | Description of works | Status | Work OK | Not OK | Not Appicable | Criteria
1 | Antenna and RF Head Installation
1.1 | Antenna type | Major |  |  |  | Correct type according to site specific radio equipment specification?
1.2 | Antenna location, Height | Major |  |  |  | Location, height according to detail design?
1.3 | Antenna fixation | Major |  |  |  | Correct type of fixation used, Mounts and brackets tight, locked?
1.4 | RF Head Mounted to Pole | Major |  |  |  | Correct type of fixation used, Mounts and brackets tight, locked?
1.5 | Antenna Grounding | Major |  |  |  | Correct Cable type, properly connected?
1.6 | RF Head Grounded | Major |  |  |  | Correct Cable type, properly connected?
1.7 | Antenna orientation | Major |  |  |  | Correct Azimuth (+)/- 2 degree (see TSVR sheet or TSVR data)
1.8 | Antenna tilt Mechanical/Electrical | Major |  |  |  | (+)/- 0,5 degrees.
1.9 | Jumper cables | Minor |  |  |  | Correct length, sensible routing, properly fixed?
1.11 | Connections to RF Head | Major |  |  |  | Correct Fiber Optic and DC connected correctly per Sector , Cables crossed?
1.12 | Connectors | Minor |  |  |  | Connectors tightened properly
1.13 | Connector sealing | Minor |  |  |  | Properly sealed, right tape used, tie wraps on both ends?
1.14 | Fiber Opticr cable run to DAP | Major |  |  |  | Properly routed in Coduit, correct cable length?
1.15 | Fiber Optic cable fixation | Minor |  |  |  | Correct type, distance between fixations, cable undamaged?
1.16 | DC cable run to DAP | Major |  |  |  | Properly routed in Coduit, cable length?
1.17 | DC cable fixation | Minor |  |  |  | Correct type, distance between fixations, cable undamaged?
1.18 | RGPS Antenna Type | Major |  |  |  | Correct type according equipment specification?
1.19 | RGPS Antenna Location, Height | Major |  |  |  | RGPS has a clear View of the Sky and it is not in the location which accumulates derbis. RGPS should be away from the Transmit Antennas
1.2 | RGPS Head and Mast are Secure | Major |  |  |  | Correct type of fixation used, Mounts and brackets tight, locked?
1.21 | Labeling | Minor |  |  |  | Correct type, on all required positions?
2 | BCU Cabinet (check against initial design)
2.1 | Equipment boxes / racks equipment spec. | Minor |  |  |  | Undamaged, properly fixed (correct material), components properly fitted?
2.2 | Configuration site-specific | Major |  |  |  | Correct configuration according to site specific Module equipment specification?
2.3 | BCU Unit is securley fix inside the Outdoor Cabinet or at 19" Rack | Major |  |  |  | Correctly installed? Air flow clearance requirement are met?
2.4 | Digital Modules Installation | Minor |  |  |  | All Cards are inserted properly
2.5 | BCU-DAP DC cables properly installed and connected | Major |  |  |  | Correctly installed? Cables Crossed?
2.6 | BCU-DAP Fiber cables properly installed and connected | Major |  |  |  | Correctly installed? Cables Crossed?
2.7 | BCU Ethernet Cable (for Backhaul) | Minor |  |  |  | Correctly installed?
2.8 | unused fiber and power ports should be covered | Minor |  |  |  | Correctly installed?
2.9 | BCU is Grounded | Major |  |  |  | Correctly installed?
2.1 | DC connections | Major |  |  |  | Power and ground connections correct size and type, presented neatly?
2.11 | Transmission connection equipment spec. | Major |  |  |  | Labelled correctly and terminated neatly?
2.12 | FiberOptic connections | Minor |  |  |  | Bulkhead connectors properly tightened, jumpers run neatly?
2.13 | Customer Alarms cables | Minor |  |  |  | Connected and terminated correctly at alarm Panel or at Customer's Alarms sensors for Indoor site?
2.14 | Labels | Minor |  |  |  | Correctly installed? All required Positions
3 | DC Power connection
3.1 | Outdoor / Indoor Rack | Major |  |  |  | Securely fixed, grounded? Is Power cable connection is correct?
3.2 | Rectifiers | Minor |  |  |  | Distribution capacity, wiring, clamps tightened, damages, inerted properly?
3.3 | Batteries | Major |  |  |  | Correct Configuration, Wiring, clamps tightened, damages, installed properly?
3.4 | Cables | Major |  |  |  | Dimension, size, correct colour coding?
3.5 | Cable run, Conduit, Through passes | Minor |  |  |  | Properly routed, cable duct / tray, fixation? Check any crossing with trunk cable.
3.6 | Termination | Major |  |  |  | Correctly executed? properly tightened?
3.7 | Labeling | Minor |  |  |  | Correct type, on all required positions?
4 | Earthing and Lightning Protection
4.1 | Antenna protection /Lightning rod | Major |  |  |  | Are all WiMAX and directional radio antennae lightning protected (45° cone)? Proper installation, highest position, no mix of materials?
4.2 | Earthing of metal parts (Part of Site preparation) | Minor |  |  |  | Tower / mast / pole(s), fence/gate, ladders/walkways/railings, support frames, etc.?
4.3 | Main Earth Pit (Part of Site preparation) | Minor |  |  |  | Properly installed, corrosion free?
4.4 | Earth bar(s) or Earth Point on tower / pole | Minor |  |  |  | Properly fixed, connected to earthing system, mix of materials?
4.5 | Proper Crimping | Minor |  |  |  | Properly executed?
4.6 | Earth Resistance (Part of Site preparation) | Major |  |  |  | Less than 1 ohm without any load.
4.7 | Equipment protection | Minor |  |  |  | Is the equipment lightning protected (45° cone)?
4.8 | Conductors ('implementation' parts) | Minor |  |  |  | Properly routed (line-of-strike), material, mix of material, bends, fixation?
4.9 | Connections ('implementation' parts) | Minor |  |  |  | All required connections done? Properly executed?
4.1 | Labeling | Minor |  |  |  | Correct type, on all required positions?
4.11 | Overall Layout | Minor |  |  |  | Overall design ok?
5 | External Alarms & Sensors (If Applicable)
5.1 | Mains failure alarm | Major |  |  |  | Sensible location, correctly mounted and wired, tested? Mains fail due to 1. Commercial Power fail 2. Low voltage and 3. High Voltage
5.2 | Rectifier Module failure alarm | Minor |  |  |  | Functional? Correctly wired?
5.3 | Intruder Alarm | Minor |  |  |  | Functional? Correctly wired?
5.4 | Low battery Alarm | Major |  |  |  | Functional? Correctly wired?
5.5 | High temperature alarm | Major |  |  |  | Functional? Correctly wired?
5.6 | AC/DC SPD fault Alarm | Major |  |  |  | Functional? Correctly wired?
5.7 | Fan Fault Alarm | Minor |  |  |  | Functional? Correctly wired?
5.8 | Labeling | Minor |  |  |  | Correct type, on all required positions?

## Snag List
PAT Date | :
Site ID | :
Site Name | :
Snag List
Sl No. | Description of snag | Responsible
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
Remarks:
Acceptance Engineer (Motorola) |  | Accepting Engineer (Customer)
Name: |  | Name:
Signature: |  | Signature: